## Slide 1: Financial Management Services (FMS) Stakeholder Meeting FMS Vendor Transition for Self-Directed Services
Community HealthChoices
February 4, 2022

## Slide 2: Agenda
Transition of Financial Management Services
Information Sessions
Payroll
EVV Training
What’s New
Tempus Website
Questions
FMS Transition
Presented by your Community HealthChoices MCOs: AmeriHealth Caritas PA CHC, Keystone First CHC, PA Health & Wellness, Inc., UPMC
AND Tempus Unlimited

## Slide 3: Transition of Financial Management Services

## Slide 4: Sharing the News!
How communications are being provided
  Monthly letters from each MCO August and September
  Monthly letters from Tempus since October
  Monthly Stakeholder meetings started in June
  Service Coordinators including information on transition in touch base discussions
  Frontline calling and texting campaign to DCWs
  PPL including messages on EVV app, portal, messaging system and in envelope stuffers
  MCOs partnering with PHLP (Pennsylvania Health Law Project) with talking points and requests to guide participants to the correct place with questions
  Common Law Employer and Direct Care Worker Transition Packet mailing in November and ongoing for new enrollments

## Slide 5: Sharing the News!
How communications are being provided
  Tempus Call-in/Online WebEx Transition Information Sessions held in November and December
  Tempus hosted In-Person Transition Sessions in December
  General Question & Answer Call-in/Online WebEx Sessions starting in January through transition
  Tempus EVV Training started in January

## Slide 6: Transition Packets for Common Law Employers and Direct Care Workers
Tempus mailed pre-populated Transition Packets with information received from Public Partnerships LLC.
Packets mailed to the Common Law Employer’s address on file.
Participant/Common Law Employer Transition Packets include:
Cover Letter
CLE Enrollment Checklist
Common Law Employer Agreement *
IRS Form 2678 - Employer/Payer Appointment of Agent *
Tempus Notice of Privacy Practices
  * Sign and Return; Requires signature of the CLE
Direct Care Worker Transition Packet sent for EACH of your DCWs. Packets include:
Cover Letter
DCW Enrollment Checklist
Direct Care Worker Agreement **
Direct Care Worker Information and Acknowledgement Form **
  ** Sign and Return; Requires signature of both the CLE and the DCW

## Slide 7: Transition Packet Mailing
Initial CLE and DCW transition packets mailed by end of November 2021
  Packets mailed to “active” or “good to go” CLEs and DCWs based on information provided by PPL.
  Packets returned to Tempus as undeliverable are being researched to make sure everyone gets a packet who should receive a packet.
  Some packets were mailed to Participants who transferred to Agency Model and no longer using self-directed services.
    Tempus and CHC-MCOs are going through the list to remove those not using self-directed services.
As new Participants and DCWs complete the enrollment process with PPL, Tempus will mail transition packets when notified of an “active” or “good to go” status through regular updates provided by PPL.
Participants who did not receive a transition packet for themselves or an active DCW, should complete a packet request on the Tempus website at https://pa.tempusunlimited.org or email Tempus at PAFMS@tempusunlimited.org or call 1-844-9TEMPUS (1-844-983-6787).

## Slide 8: Preparing for What’s Ahead
Tracking of packets to ensure individualized outreach for no response or corrections needed
Pre-populated forms – easy to complete
  Low percentage of corrections – doing individual outreach for corrections
MCOs socializing information for all participants throughout organizations
MCOs preparing internally with staff training and education, as well as team updates

## Slide 9: Transition Progress – Packets
Transition Packet Statistics
  48% of CLE packets and 40% of DCW packets were returned
  Tempus planning to re-mail transition packets to all individuals who have not returned their packet
  Transition packet requests can be submitted on the Tempus website
  During EVV training sessions, CLEs and DCWs reminded to return their packet
Transition Packets returned that are incomplete
  Tempus is identifying categories of issues and doing targeted communication that includes text, email and phone messages
Transition Packets need to be returned and complete prior to first payroll check on April 1, 2022

## Slide 10: Transition Progress – Call Center
Call Center Stats and Activity
  Dedicated Pennsylvania toll-free phone line
  Average wait time is 6 minutes as of yesterday (2/3/2022)
Staffing Plan for Call Center
  Hiring of call center staff is ongoing
  Professional trainer hired to decrease training time for new hires
  Developing tiers of support for Customer Relations Department
How is Tempus managing call backs and responses to emails
  Auto call back feature will be implemented February 4
  Most call backs made by Customer Relations staff after 4:30 pm when inbound calls end
  Emails are reviewed and routed to the appropriate department for a response

## Slide 11: Transition Progress – Call Center
Tempus anticipates call volume will spike March 6 and again on March 13 when time needs to be submitted to Tempus
Expect incoming calls from individuals who didn’t return a packet or attend EVV training
Tempus plan to assist CLEs and DCWs
  Dedicated group to handle EVV questions
  Additional Q&A sessions for non-EVV questions
  “How to” Guides on how to submit and approve time worked will be posted to Tempus website
  Recording of EVV Training sessions will be posted to the Tempus website soon
  Scheduled EVV sessions will continue through end of March
  Telephony option available

## Slide 12: Information Sessions

## Slide 13: Call-in and Online Information Sessions
Tempus will host one hour Question and Answer Call-in and Online WebEx sessions through the transition to answer general questions from Participants, CLEs and DCWs.
  Login Information included in the monthly communication and posted to the Tempus website at https://pa.tempusunlimited.org/.
  Please note: These are NOT EVV training sessions.

## Slide 14: Payroll

## Slide 15: Payroll Timeline
Tempus will issue payroll checks starting April 1, 2022
Payroll schedules for Participants will remain the same
  Participants on Schedule B with PPL
    Services beginning with pay period 3/6–3/19/2022 will be submitted to Tempus
    Payment date 4/1/2022
    The payroll period of 3/20-4/2/2022 will be paid on 4/8/2022
    Check dates will be every 2 weeks thereafter (4/22; 5/6; 5/20; etc.)
  Participants on Schedule A with PPL
    Services beginning with pay period 3/13–3/26/2022 will be submitted to Tempus
    Payment date 4/1/2022
    Check dates will be every 2 weeks thereafter (4/15; 4/29; 5/13; etc.)

## Slide 16: EVV Timesheet Submission and Approval Process Training

## Slide 17: Timesheet Submission & Approval Process
Electronic Visit Verification (EVV) requirements do not change. Changes to process include:
  New app to clock in and clock out
  New process for DCWs to review and submit time to CLE for approval
  New approval process for CLEs
  New phone system option for DCWs and CLEs to record and approve time
Important information regarding Tempus user accounts:
  All CLEs and DCWs must have a unique email address
  CLEs and DCWs will need to provide Tempus their email address
  To provide email address to Tempus, visit https://pa.tempusunlimited.org/ and click on the email survey link, answer the questions, and submit the form
  “How to” videos explaining how to get free email accounts with Google, Microsoft and Yahoo! on Tempus website
Every Common Law Employer and Direct Care Worker will need to be trained.

## Slide 18: Timesheet Submission & Approval Process
Beginning January 10, 2022, Tempus began to host multiple training sessions for CLEs and DCWs.
Training will be conducted through:
  Online WebEx Sessions
  In-person Sessions
  How-to Guides and Training Videos will be posted to the Tempus website
Training topics include:
  How to download and use the Tempus EVV app to clock in and clock out
  How to use the Tempus portal to submit time worked, edit a shift and create a manual entry
  How to use Tempus phone system to clock in and clock out
  How to approve or reject a shift
  How to use the Tempus portal to view timesheet and payment information
  How to obtain a user account to access the Tempus EVV app and Tempus portal

## Slide 19: Timesheet Submission & Approval Process
Tempus will host 90 minute Online WebEx sessions from 1/10/2022 through 4/2/2022 for CLEs and DCWs to learn how to submit and approve time worked.
  Login Information included in the monthly communication to CLEs and posted to the Tempus website at https://pa.tempusunlimited.org/.

## Slide 20: What’s New

## Slide 21: What’s new with Tempus
DCWs will have three payment options to receive their paycheck
  Direct Deposit
  Paper Check
  New – U.S. Bank Debit Card option
    Tempus will assist with DCW enrollment for the Debit Card
Call center call back feature
Enhanced Training for Direct Care Workers
  The direct care workforce has a challenging job
  Considerable skill level is needed to provide direct care
  Advances skills and knowledge
  It advances productivity and performance
  Training develops work ethics, relationships, and safety
  It standardizes work processes while recognizing unique nature of each participant
  It boosts morale and improves worker satisfaction
  Participants will feel impact of elevated service

## Slide 22: Tempus Website

## Slide 23: Tempus Informational Website
Website address: https://pa.tempusunlimited.org
  This is your best source of information
Check Frequently: Information and updates from the CHC-MCOs and from Tempus will be posted to the Documentation section
Webinars and In-person sessions: Schedule posted with important webinars and in-person sessions to assist you with submitting and approving time worked
The FAQs will be updated as we provide more information to Participants, Common Law Employers, and Direct Care Workers

## Slide 24: Pennsylvania In-State Hiring Initiative
Tempus is hiring remote and in-office staff for Pennsylvania
Tempus is opening three offices in Pennsylvania
  Pittsburgh Area
  Central Pennsylvania
  Philadelphia area
Individuals with lived experience or an understanding of self-direction would be valuable
Please check the Tempus website frequently for job openings:
  Website: https://tempusunlimited.org

## Slide 25: Questions?